## Cover and Instructions
Fayetteville Public Work Commission Oracle CCS Implementation Project Services Scope
Services Scope. PWC has defined the services required to implement the Provider's solution.
Instructions to Providers:
Provider Name: | <<PLEASE INSERT NAME>>
Implementation Services | PWC seeks standard Implementation Services as part of this project. PWC envisions the Implementation Services to be a defined set of activities delivered collectively, but led by the Provider and done so in a pre-defined and agreed to project timeline. These services are required, but PWC is open to how each provider approaches the process and the methodology to accomplish the requirements. PWC has provided the service being requested (at a high level) and has indicated their preference on who they would like to take primary responsibility for delivery of the service. Please respond to each line item as to whether you have included the Service in your price - YES or NO - and provide additional detail or commentary to help PWC better understand what services you are able to provide, how you will provide them, and to what extent. Providing additional details and comments will be looked upon favorably.

## Implementation Services Scope
Item # | Service Type | Service Area | Service Scope Description | Responsible to Deliver | Included in Price (Y/N) | Comments/Notes Provide details on methodology and how each service is accommodated. When possible, include an estimated time frame.
1 | Implementation Services | Build and Configure - Configuration | The Provider shall configure the application based on client approved design. | Provider
2 | Implementation Services | Build and Configure - Customization | The Provider shall perform client specific modifications based on client approved design. | Provider
3 | Implementation Services | Build and Configure - Dashboards | The Provider shall configure dashboards to support analysis and data insights across all key functional areas. | Provider
4 | Implementation Services | Build and Configure - Integration | The Provider shall develop client specific interfaces/API's based on client approved design. | Provider
5 | Implementation Services | Build and Configure - Integration | The Provider could manage third parties for integrations. | Provider
6 | Implementation Services | Build and Configure - Report Development | The Provider shall develop client specific reports based on client requirements and approved design. | Provider
7 | Implementation Services | Data Migration/ Conversion | The Provider shall provide a solution that enables FPWC to access historical data beyond the converted 7-year period through a read-only database reference capability. | Provider
8 | Implementation Services | Data Migration/ Conversion | The Provider shall develop a comprehensive Data Conversion Plan including mapping and results documentation. | Provider
9 | Implementation Services | Data Migration/ Conversion | The Provider shall provide lifecycle management to maintain the mandated required amount of data. | Provider
10 | Implementation Services | Data Migration/ Conversion | The Provider shall write extraction scripts to extract the data from source systems. | Provider
11 | Implementation Services | Data Migration/ Conversion | The Provider shall identify and prioritize data cleansing requirements. | Provider
12 | Implementation Services | Data Migration/ Conversion | Performs data cleansing for source data that cannot be handled in extraction or migration. | FPWC
13 | Implementation Services | Data Migration/ Conversion | The Provider shall perform data cleansing using scripts. | Provider
14 | Implementation Services | Data Migration/ Conversion | The Provider shall provide data cleansing guidance to Utility. | Provider
15 | Implementation Services | Data Migration/ Conversion | The Provider shall load the data into the application(s). | Provider
16 | Implementation Services | Data Migration/ Conversion | The Provider shall provide a solution that enables migration of the required historical data into application. | Provider
17 | Implementation Services | Data Migration/ Conversion | The Provider shall obtain approval from FPWC on final data migration results prior to Go-Live/Cutover, to include comparison results of source vs. target for migrated data (various data domains). | Provider
18 | Implementation Services | Data Migration/ Conversion | The Provider shall translate the data into load ready format (may include data cleansing rules). | Provider
19 | Implementation Services | Design | The Provider shall provide a workshop schedule for design workshops with agendas. | Provider
20 | Implementation Services | Design | Provides interface specifications of existing interfaces. | FPWC
21 | Implementation Services | Design | The Provider shall conduct design workshops, leverage CCS native workflow capabilities, and identify gaps in business processes from industry best practices for end to end processes. | Provider
22 | Implementation Services | Design | Schedules workshops and ensures the correct participants attend. | FPWC
23 | Implementation Services | Design | The Provider shall provide architecture diagram for final integrations with CIS. | Provider
24 | Implementation Services | Documentation | The Provider shall provide system reference guides, materials, documentation of the system and processes. | Provider
25 | Implementation Services | Documentation | The Provider shall document client specific configurations and modifications. | Provider
26 | Implementation Services | Documentation | The Provider shall document client specific technical design - end to end functionality documentation and seek signoff on deliverable approval. | Provider
27 | Implementation Services | Documentation | The Provider shall provide system release notes ahead of release. | Provider
28 | Implementation Services | Documentation | The Provider shall provide user documentation and training materials. | Provider
29 | Implementation Services | Documentation | The Provider will provide Oracle CCS business process documentation. | Provider
30 | Implementation Services | Environment Management | The Provider shall provide recommended network configuration advice. | Provider
31 | Implementation Services | Environment Management | The Provider shall perform infrastructure sizing and provides infrastructure recommendations. | Provider
32 | Implementation Services | Environment Management | Procure/provision infrastructure/infrastructure services for development, testing, production and for reporting/data access of a production environment. | FPWC
33 | Implementation Services | Environment Management | The Provider shall perform base product installation. | Provider
34 | Implementation Services | Environment Management | Performs network configuration and changes up to Provider specifications and line of demarcation. | FPWC
35 | Implementation Services | Environment Management | The Provider shall manage production and non production instances during the project, to include scheduling requests. | Provider
36 | Implementation Services | Environment Management | The Provider shall manage configuration and modification across the FPWC's specific non-production instances/environments. | Provider
37 | Implementation Services | Go Live Readiness/Go Live | Defines Go-Live criteria. | FPWC
38 | Implementation Services | Go Live Readiness/Go Live | The Provider shall meet Go-Live Criteria. | Provider
39 | Implementation Services | Go Live Readiness/Go Live | Provide support to the development of the cutover plan. | Provider
40 | Implementation Services | Go Live Readiness/Go Live | The Provider shall manage system cutover. | Provider
41 | Implementation Services | Organizational Change and Readiness | Identifies, tracks and resolves organizational change impacts. | FPWC
42 | Implementation Services | Organizational Change and Readiness | The Provider shall support identification of changes and manage the change impact matrix, to include detail by role. | Provider
43 | Implementation Services | Organizational Change and Readiness | Organizational Change Management - identifies and prepares the FPWC for changes. | FPWC
44 | Implementation Services | Organizational Change and Readiness | The Provider shall conduct core team or implementation training. | Provider
45 | Implementation Services | Organizational Change and Readiness | The Provider shall conduct "Train the Trainer" training, ability to leverage schedule, agendas, attendees for end user training. | Provider
46 | Implementation Services | Organizational Change and Readiness | The Provider shall support development of end-user Readiness Assessments including templates and evaluation criteria. | Provider
47 | Implementation Services | Organizational Change and Readiness | Defines and delivers Readiness/Competency Assessment to End Users. | FPWC
48 | Implementation Services | Post Go Live Hypercare | The Provider shall provide level 2 and 3 support for no less than 3 complete end to end billing cycles (3 months). | Provider
49 | Implementation Services | Post Go Live Hypercare | Performs additional end user training. | FPWC
50 | Implementation Services | Post Go Live Hypercare | The Provider shall support additional End User Training post go-live. | Provider
51 | Implementation Services | Post Go Live Hypercare | The Provider shall perform defect analysis and resolution during the system acceptance period. | Provider
52 | Implementation Services | Post Go Live Hypercare | Provides level one support to end users. | FPWC
53 | Implementation Services | Project Management | Manages the project budget. | FPWC
54 | Implementation Services | Project Management | Produces and presents weekly status reports to PWC Project Manager that includes progress update, risks, issues, and escalations. | Provider
55 | Implementation Services | Project Management | Supports PWC team presentations to project stakeholders. | Provider
56 | Implementation Services | Project Management | Provides a point of contact and process for project escalations. | FPWC
57 | Implementation Services | Project Management | The Provider shall provide a traceable process that ensures requested business process improvements, features and functions are delivered. | Provider
58 | Implementation Services | Project Management | The Provider shall create and maintain the project plan in Smart Sheets. | Provider
59 | Implementation Services | Project Management | The Provider shall a dedicated project manager with Oracle CCS experience to manage resources and schedule for the duration of the project. | Provider
60 | Implementation Services | Project Management | The Provider shall create and maintain the project RAID (Risks, Actions, Issues and Decisions) log. | Provider
61 | Implementation Services | Project Management | Communicates organizational structure for the project and the stakeholders of the project. | FPWC
62 | Implementation Services | Project Management | Implements a scope change order process to monitor increases and reductions in scope and expenditure. | Provider
63 | Implementation Services | Project Management | Follows defined change order process. | Provider
64 | Implementation Services | Project Management | Conducts monthly steering committee meetings to communicate project health to stakeholders. | FPWC
65 | Implementation Services | Project Management | The Provider shall educate project team and stakeholders on implementation methodology and approach. | Provider
66 | Implementation Services | Project Management | Provider shall designate a Point of Contact (POC) for escalations, and FPWC shall designate a corresponding POC. All escalated issues shall be communicated between the respective POCs. | Provider
67 | Implementation Services | Project Management | Provider shall gain PWC approval on all deliverables. | Provider
68 | Implementation Services | System Acceptance | The Provider shall create a system acceptance criteria defined in contract that accounts for the resolution of all severity 1 defects, compliance with all specifications and requirements, and confirmation that all project artifacts (specifications, training material, and documentation, etc.) are provided. | Provider
69 | Implementation Services | System Acceptance | The Provider shall provide appropriate resources for knowledge transfer. | Provider
70 | Implementation Services | System Acceptance | The Provider shall provide level 2 support to FPWC for at least 90 days post Go-Live. | Provider
71 | Implementation Services | System Acceptance | The Provider shall provide knowledge and responsibility transfer to PWC staff using the Provider's proposed process. | Provider
72 | Implementation Services | Testing | The Provider shall deliver a master test strategy/plan that defines testing phases, scope, roles/responsibilities, environments, entry/exit criteria, defect triage/escalation, and sign-off requirements. | Provider
73 | Implementation Services | Testing | The Provider shall document all test results, to include a consolidated audit of migrated data (Counts, source/target table loaded) and comparison results (target vs source) for all data domains. Artifacts must be suitable for audit, including scrips, results, reconcilations, and defect logs. | Provider
74 | Implementation Services | Testing | The Provider shall test and document error handling, retry logic, replay/reprocessing procedures, and operational recovery steps for each integration. | Provider
75 | Implementation Services | Testing | The Provider shall perform load testing to make sure CCS environment can support production loads. | Provider
76 | Implementation Services | Testing | The Provider shall perform unit testing and provide documentation. | Provider
77 | Implementation Services | Testing | The Provider shall write and execute integration test scripts. | Provider
78 | Implementation Services | Testing | The Provider shall lead integration testing. | Provider
79 | Implementation Services | Testing | The Provider shall work directly with third party applications to enable integration testing. | Provider
80 | Implementation Services | Testing | The Provider shall coordinate and execute testing with the bill print vendor, including file layout validation, control totals, duplicate suppression, rerun procedures, and delivery timelines. | Provider
81 | Implementation Services | Testing | The Provider shall define approach, perform and execute parallel testing. | Provider
82 | Implementation Services | Testing | Writes all FPWC/Utility specific user acceptance test scripts. | Provider
83 | Implementation Services | Testing | The Provider shall review and validate expected functionality defined within user acceptance test scripts. | Provider
84 | Implementation Services | Testing | Executes user acceptance testing. | FPWC
85 | Implementation Services | Testing | The Provider shall support security and access testing, including role-based access validation, least-privilege verification, segregation of duties validation, and audit logging verification for CCS and integrated components where applicable. | Provider
86 | Implementation Services | Testing | The Provider shall provide system test scenarios and scripts - Unit, Functional, Integration. | Provider
87 | Implementation Services | Testing | The Provider shall provide testing support. Preferred near real time responses to support questions and testing execution. | Provider
88 | Implementation Services | Testing | The Provider shall document and resolve defects identified during testing. | Provider
89 | Implementation Services | Testing | The Provider shall utilize PWC OUTA to track testing results and progress; only automation testing scripts. | Provider
90 | Implementation Services | Testing | The Provider shall execute Regression Testing with PWC support. | Provider
91 | Implementation Services | Testing | The Provider shall utilize PWC Azure DevOps for manual test scripts and integration test scripts. | Provider
92 | Implementation Services | Testing | The Provider shall follow SLAs for testing during the implementation. | Provider
93 | Implementation Services | Testing | The Provider shall use Oracle Utilities Testing Accelerator (OUTA) for automated testing activities as directed by FPWC. | Provider
94 | Implementation Services | Testing | The Provider shall facilitate testing governance (status meetings, daily execution stand-ups during SIT/UAT/Parallel, and defect triage meetings). | Provider
95 | Implementation Services | Testing | The Provider shall log and manage defects in Azure DevOps, using access provided by FPWC. | Provider
96 | Implementation Services | Training | The Provider's training plan shall include all in scope applications and integrations, to include CCS, OUDI, and OFS. | Provider
97 | Implementation Services | Training | Conducts end-user training. | FPWC
98 | Implementation Services | Training | The Provider shall support end user training - "expert in the room". | Provider
99 | Implementation Services | Training | The Provider shall conduct application/project team training. | Provider
100 | Implementation Services | Training | The Provider shall provide application training documentation. | Provider
101 | Implementation Services | Training | The Provider should provide end-user training documentation. | Provider

## Pick Lists (hidden)
Respondsible to Deliver | Included in Price | Service Area
FPWC | Yes
Provider | No